## Revision
GOAL ID# | Action Items | Timing | AK Milestones | Target Dates | AK POC
EBFM Principle 1: Implement Ecosystem Level Planning
1a1 | Establish EBFM Point of Contact at each Regional Office, Fisheries Science Center, and HQ Offices | Short | Kerim Aydin (AFSC), Bridget Mansfield (AKR), Diana Evans (NPFMC) | Complete | Kerim Aydin, Brdiget Mansfield, Diana Evans
1a2 | Develop National and Regional EBFM engagement strategies | Short | Initial engagement with Council through scoping of Bering FEP (2014-2016). Bering FEP to include extensive engagement strategy | 2018-12-01 | Bering FEP team
1a3 | Develop best practices where there are overlapping jurisdictions | Mid | Bering FEP will highlight where there are overlapping jurisdictions, and existing mechanisms for coordination among different authorities, and whether there is need/opportunity for improvement. | Complete | Bering FEP team
1a5 | NOAA Fisheries supports any Ecosystem Plan Development Teams, Ecosystem Committees (or equivalent groups) that Councils establish | Continuing | NPFMC Bering Sea FEP is a major guiding document for AK EBFM processes. The FEP is being developed jointly by the Bering FEP team (science and technical) and the Council's Ecosystem Committee (policy). | Complete | Bering FEP team
1a6 | Continue to explore tradeoffs in the context of EBFM issues and relevant statutory mandates | Mid | Analysis and summary of statutory mandates is part of Bering FEP | Complete | Bering FEP team
1b1 | Establish Fishery Ecosystem Plan Coordinator/Analyst for each NOAA Fisheries Regional Office and in appropriate Headquarters Office | Mid | The current Alaska Region EBFM POC is the Fishery Ecosystem Plan Coordinator/Analyst for the Alaska Region. | Complete | Anne Marie Eich
1b2 | Review and develop inventory of existing Fishery Ecosystem Plans and Ecosystem Considerations in fishery management plans, documenting best practices | Short | While this is a national-level milestone, the Bering Sea FEP will review and include FEP best practices. | Complete | Bering FEP team
1b3 | Assist Councils, Commissions, regional fisheries management organizations, and other bodies as requested, in their development of new, or revision of existing Fishery Ecosystem Plans | Continuing | Bering Sea FEP, adopted by the Council in December 2018, includes explicit climate module, will substantially guide incorporation of climate and ecosystem information going forward. Climate-enhanced SAs implemented or in development for key stocks. | 2018-12-01 | Bering FEP team
EBFM Principle 2: Advance our understanding of ecosystem processes
2a1 | Advance resources to conduct EBFM | Continuing | Research tracking (from Council request to NOAA research to Council delivery) being implemented as part of Bering FEP | 2018-12-01 | Kerim Aydin
2a2 | Develop capacity for NOAA Fisheries to conduct end-to-end ecosystem studies | Mid | Partnership of North Pacific Research Board's Integrated Ecosystem Research Programs (Bering and GOA) and NOAA AK-IEA program for 3-5 year ecosystem studies | BSIERP concluded 2014; GOAIERP to conclude 2019 | North Pacific Research Board
|  | Mid | At AFSC, there is significant communication between groups (e.g. between FATE, IEA, SAIP scientists) promoted through regular activities (e.g. RPA and IEA workshops). An example collaborative project (FATE, SAAM and NCSS) is the ACLIM project. | ongoing | AFSC leadership
2a3 | Conduct biennial EBFM Science & Management Conference | Mid | Regional IEA workshop conducted biennially (alternating with national IEA meeting) | First workshop completed Spring 2018 | Kerim Aydin
2a4 | Develop and maintain core data and information streams | Continuing | Multiple surveys (groundfish and ecosystem surveys) coordinated through IEA, the AFSC Recruitment Processess Alliance (RPA), and NP observer program. | ongoing | AFSC leadership
|  | Mid | Bering FEP is also evaluating ways to better incorporate local knowledge and traditional knowledge as part of fishery management process (action module to the FEP). | 2019 | Bering FEP team
2b2 | Establish routine, regular and dynamic reporting of indicator-based ecosystem status reports for each large marine ecosystem | Mid | All 5 LMEs in AK Region have ESRs updated on a regular schedule (annually for EBS and GOA, every other year for AI and high Arctic- Chukchi and Beaufort Seas). Development and improvement of ecosystem indicators is continual/ongoing active research. https://access.afsc.noaa.gov/reem/ecoweb/Index.php | ongoing | Stephani Zador
EBFM Principle 3: Prioritize vulnerabilities and risks of ecosystems and their components
3a1 | Conduct Systematic Risk Assessments for relevant NOAA regional ecosystems | Long | A risk assessment for the Aleutian Islands was conducted as part of the Aleutian Islands FEP. A similar exercise is planned for the Bering Sea as part of the Bering FEP. | ongoing | Kerim Aydin
3a2 | Explore protocols for conducting regional habitat risk assessments for those areas known to serve important ecological functions for multiple species groups or will be especially vulnerable or important in the face of climate change | Mid | 2-year Bering Sea CVA project nearing completion/publication. Tasking/funding for GOA CVA uncertain. | 2018 | Paul Spencer
|  | Mid | Bering Sea climate vulnerability analysis included evaluating essential fish habitat (EFH) shifts under future climate scenarios for the Bering Sea, using ACLIM and species distribution models adopted during the EFH 2015 5-year review and update for Alaska. | 2019 | Paul Spencer, James Thorson
|  | Continuing | Regional niche overlap analysis of EFH species distribution model-based maps to identify locations of EFH overlap for species life stages as a measure of regional habitat risk assessment. | ongoing | Jodi Pirtle James Thorson
3b1 | Ensure that factors which impact 800+ US managed species are being considered | Continuing | Robust system for implementing harvest control rules for groundfish and crab ongoing; includes ecosystem considerations for stocks. | ongoing | Anne Hollowed
3b2 | Conduct Habitat Assessment Prioritization for all NOAA Fisheries regions | Short | Habitat Assessment Prioritization for Alaska Stocks was completed in 2017 (doi:10.7289/V5/TM-AFSC-361). | ongoing | Bob McConnaughey, Matt Eagleton
3b3 | Conduct Fishing Community vulnerability assessments for all NOAA Fisheries regions | Short | AK community assessment/website ongoing work | ongoing | Steve Kasperski
3c1 | Initiate Endangered Species Act section 7 consultations for any fishery management action that may affect listed species, and reinitiate consultations as warranted | Continuing | Assess need for consultation on every new FMP amendment or regulatory amendment | ongoing | Anne Marie Eich
3d1 | Evaluate stock-level fishing impacts to essential fish habitat (EFH) | Continuing | The Alaska EFH 5-year review and update of 2015 advanced the fishing-effects model and fishing impacts analysis, using new species-distribution model-based maps of EFH. Stock-level impacts to EFH from fishing activities were analyzed by stock assessment authors using a new, quantitative threshold-based process, where potential need for conservation actions could be further evaluated. The revised fishing-effects model and review process were adopted with the current EFH update. | ongoing | John Olson, James Thorson
EBFM Principle 4: Explore and address trade-offs within an ecosystem
4a1 | Assess and bolster ecosystem and living marine resource modeling needs in each fishery science center | Short-Mid | Limited gap analysis for Bering Sea being performed as part of Bering FEP. AFSC is in the process of developing a process to ensure that the highest priority marine mammal species are being assessed at the PR-SAIP Tier III level. Further, the AFSC implementation of the NMFS adopted PBR protocol provides a sort of annual GAP analysis. | ongoing | AFSC leadership
|  | Short-Mid | Internal model priority/development planning part of IEA 3-year planning | spring 2019 | Kerim Aydin
4a2 | Development of an EBFM analytical toolbox that includes ecosystem modeling tools and best practices; data-poor qualitative and semi-quantitative tools; and related decision support tools | Mid | AK Bering IEA has focused on developing and maintaining an extensive modeling suite across many tools (Rpath, ecosim, size-structured, multispecies statistical, oceanographic, bioenergetics) | ongoing | Kerim Aydin
|  | Mid | An action module of the Bering FEP is to develop best practices for incorporating local and traditional knowledge as part of fishery management process. Among other things, the module will explore co-production of knowledge. | 2019 | Bering FEP Team
4a3 | Encourage and expand the use of multi-model inference | Continuing | Alaska Climate (ACLIM) project extends multi-model inference to climate forecasts | ongoing | Kirstin Holsman
4a4 | Establish suitable review venues and deliberative bodies for ecosystem models and associated information in each fishery science center region | Mid | EBFM models are part of CIE review cycle for AFSC - multispecies statistical model CEATTLE to be reviewed in 2018 | ongoing | Kirstin Holsman
4b1 | Develop functional system-level management strategy evaluations | Mid | ACLIM project is performing multi-model MSE analysis for harvest strategies in the Bering Sea. | 2019 | Kirstin Holsman
|  | Mid | New MSE hire has worked collaboratively with teams to develop priorities. The AFSC has a number of scientists trained in MSEs. | ongoing | Curry Cunningham
4b2 | Explore novel Harvest Control Rules (HCRs) and develop associated guidelines, as appropriate and consistent with National Standards, especially to test & explore robust Ecosystem Level strategies | Long | ACLIM project is performing multi-model MSE analysis for harvest strategies, including novel, stakeholder-driven strategies | 2019 | Kirstin Holsman
| Study and consider the effects of prey removals on listed and non-listed marine mammals | Continuing | Multiple diet and energetics studies | ongoing | Jon Kurland
EBFM Principle 5: Incorporate ecosystem considerations into management advice
5a1 | Delineate, evaluate, and explore best practices for estimating and using system-wide or aggregate group harvest limits, eco production measures, and other ecosystem level reference points, to inform management decisions | Mid | Developing multi-model inference suite for examining guild-level limits for EBS | ongoing | Kerim Aydin, Alan Haynie
|  | Mid | ELRPs in place for Bering Sea and GOA. Analysis of climate variability effects on Bering ELRP underway as part of ACLIM - multiple ecosystem reference points that include indirect and cumulative effects being investigated (Bering only) as part of IFRAME project. | ongoing | Kerim Aydin, Alan Haynie
|  | Mid | Portfolio metrics (system-level properties) to be introduced to ESRs from FY18-FY20. | 2020 | Stephani Zador
|  | Continuing | Risk tables included in each stock assessment that ranks concerns about model structure, population dynamics and ecosystem concerns that are not addressed in the recommended stock assessment model. | ongoing | Martin Dorn, Stephani Zador
5b1 | Develop and track fishery stock status indices that denote when ecosystem considerations are used | Mid | Species-specific ecosystem and socio-economic profiles (ESPs) are in development as appendices to stock assessments. These will include quantifiable metrics relating ecosystem indicators to managed stocks, allowing for the development of reference points and threshold delineation. The prototype has been completed for sablefish. Three annual workshops (2019-2021) have been funded by AFSC to develop ESPs for other stocks. | ongoing | Kalei Shotwell
|  |  | The risk tables included in each stock assessment that rank concerns about model structure, population dynamics and ecosystem concerns that are not addressed in the recommended stock assessment model, will be used to track when ecosystem considerations are used to recommend allowable biological catch below the maximum permissable. | ongoing | Martin Dorn, Stephani Zador
5b2 | Support consistent and effective implementation of the NS1 guidelines, which includes guidance on incorporating ecosystem information into stock management | Mid | Ecosystem considerations are incorporated into stock assessments and presented during the review process (groundfish and crab Plan Teams and SSC) - Bering FEP is formalizing inclusion and review process | ongoing | Bering FEP team
5b3 | Identify best practices for incorporating ecosystem considerations into management decisions | Short-Mid | Best practices indentification is chapter of Bering FEP |  | Bering FEP team
5b4 | Establish ecosystem-related Terms of References for stock assessments, stock assessment reviews, and support ecosystem-related terms of reference for status review groups, harvest control rules, and science and statistical committee review processes | Mid | chapter of FEP | Complete | Bering FEP team
| Integrate EFH text descriptions and maps with the new Ecosystem-Socioeconomic Profiles (ESP) in the Stock Assessment and Fishery Evaluation (SAFE) Reports for Alaska stocks to track habitat-based stock-level indicators | Mid | An ESP was completed for Alaska Sablefish, Appendix 3C of 2017 SAFE Report (Hanselman et al. 2017). The ESP evaluates ecosystem considerations, including habitat descriptions and EFH species distriution model-based maps. ESPs are in development for other Alaska stocks. | ongoing | Kalei Shotwell, Jodi Pirtle
5c1 | Explore protocols for considering ecosystem-level information in EFH 5-year reviews, identifying ecosystem-level habitat areas of particular concern, and setting habitat conservation objectives and/or indicators | Continuing | Habitat conservation objectives are identified in the groundfish FMPs. The Council's HAPC process considers ecosystem-level information in determining appropriate HAPC areas. | ongoing | Matt Eagleton, Diana Evans
|  | Continuing | The Alaska EFH 5-year review of 2015 adopted a species-distribution modeling (SDM) approach to EFH maps using regional habitat predictor variables and advanced the fishing-effects model and impacts analysis. EFH Level 1 was defined or advanced to Level 2 for life history stages of most North Pacific Council managed species. A similar ecosystem-based approach to EFH will be applied to future 5-year reviews and updates (doi:10.7289/V5/TM-F/AKR-15). | ongoing | Jodi Pirtle, James Thorson
|  | Continuing | The Alaska EFH Research Plan was revised in 2017, following the EFH review and update of 2015. Significant revisions include a process for multi-year projects to advance EFH Level 3 information, and continued progress on model-based updates to EFH Levels 1 and 2 where needed for North Pacific Council managed species. EFH Research is funded through an internal process between NMFS AKR and AFSC (doi:10.7289/V5/AFSC-PR-2017-05). | ongoing | Jodi Pirtle, James Thorson
|  | Continuing | The Alaska EFH 5-year review of 2015 introduced an ecosystem-based approach to evaluate impacts to EFH from non-fishing activities in Alaska. A new report section summarizes the current understanding of potential impacts to EFH from climate change and ocean acidification. A similar approach will be applied to evaluate non-fishing impacts in future updates to EFH (doi:10.7289/V5/TM-F/AKR-14). | ongoing | Matt Eagleton
5c3 | Evaluate ecosystem effects of offshore aquaculture | Long |  | ongoing | Bob Foy, Bill Hines
5c5 | Review long-term protected species recovery and rebuilding plans to ensure they account for the potential effects of near-term and long-term climate change, particularly relating to alterations to food web structure | Long |  | ongoing | Jon Kurland
EBFM Principle 6: Maintain Resilient Ecosystems
6a1 | Evaluate and Track Ecosystem-level reference point to assess changes in ecosystem-level resilience | Continuing | Several guild-level indicators tracked in ESR, including several new human dimensions indicators (new in 2017)and ecosystem health indicators (new in 2018); more under development | ongoing | Stephani Zador, Steve Kasperski
6a2 | Evaluate, conduct and track ecosystem goods and services valuation methods and best practices | Mid | The provision of goods and services by LME, broken out by guild, are now included in the ESR. Many others are included in the Econ SAFE (economic status report). AK IEA member leads the NMFS Economic Valuation Working Group to advance best practices and is actively working on several manuscripts related to the non-market value of marine resources. | ongoing | Steve Kasperski
6a3 | Develop best practices for tradeoff evaluation with respect to overall ecosystem and community resilience and well-being | Mid | Bering FEP documenting current practice for evaluating ecosystem, community resilience, well-being, and opportunities for improvement | ongoing | Kerim Aydin, Anne Marie Eich, Diana Evans
6b1 | Explore community health and well-being socio-economic metrics | Mid | Several included in the ESR, with notable expansion of human dimensions indicators begining in 2017. We have recently updated the Econ SAFE with community fisheries participation indices and several additional metrics on health and social vulnerability are under development. | ongoing | Steve Kasperski
6b2 | Adopt community vulnerability analyses to a broader range of cumulative factors | Mid | These are annual produced in the Econ SAFE for fisheries engagement, and have been used in the 20-year review of the halibut and sablefish IFQ Program and 10-year review of the BSAI Crab Rationalization Program. | ongoing | Steve Kasperski
6b3 | Track community health, well-being and vulnerability socio-economic metrics | Mid-continual | Several included in ESR and annually in the Econ SAFE. Notable expansion of human dimensions indicators in the ESR begining in 2017. Additionally, individual community snapshots of communities social, economic, and demographic information (including social indicators of community vulnerabiltiy) can be found on the AFSC website: https://www.afsc.noaa.gov/REFM/Socioeconomics/Projects/communities/snapshots.php. | ongoing | Stephani Zador, Steve Kasperski